## Project schedule
| Cybersecurity AI RMF Tool |  |  |  |  | Project start: |  |  |  | 2024-09-25
Western Washington University
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
| TASK | ASSIGNED TO | PROGRESS | START | END | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
[6 empty] | 2024-01-07 | 2024-08-14 | 15-21 | 22-30 | 2024-01-07 | 2024-08-14 | 15-21 | 22-31 | 2024-01-07 | 2024-08-14 | 15-21 | 22-30 | 2024-01-07 | 2024-08-14 | 15-21 | 22-31 | 2024-01-07 | 2024-08-14 | 15-21 | 22-31 | 2024-01-07 | 2024-08-14 | 15-21 | 22-28 | 2024-01-07 | 2024-08-14 | 15-21 | 22-31 | 2024-01-07 | 2024-08-14 | 15-21 | 22-30 | 2024-01-07 | 2024-08-14 | 15-21 | 22-31 | 2024-01-07 | 2024-08-14 | 15-21 | 22-30
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Client Reach Out | Colson Swope | 100% | 2024-09-25 | 2024-10-07 | bar: September WK4 to October WK1
| RMF Research | All Team Members | 100% | 2024-09-25 | 2024-12-13 | bar: September WK4 to December WK2
| NIST Research | Ripken Stork | 100% | 2024-10-07 | 2024-10-09 | bar: October WK2 to October WK4
| AI Model Research | Jonathan Ly | 100% | 2024-10-09 | 2024-12-13 | bar: October WK2 to December WK2
| New Member Initiation | Slate Colebank | 100% | 2024-10-31 | 2024-11-03 | bar: October WK4 to November WK1
Planning and design
| SRS | All team members | 100% | 2024-11-05 | 2024-12-11 | bar: November WK1 to December WK2
Execution
| AI Integration | Jonathan Ly Slate Colebank | 100% | 2024-01-08 | 2025-03-21 | bar: January WK2 to March WK3
| Data Collection System | Ripken Stork Colson Swope | 100% | 2024-01-08 | 2025-03-21 | bar: January WK2 to March WK3
| Web GUI | RIpken Stork Colson Swope | 100% | 2025-03-07 | 2025-04-07 | bar: March WK1 to April WK1
| Move Application to Cyber Range | All team members | 98% | 2025-02-04 | 2026-02-10 | bar: February WK1
| Backend Updates** | TBD | 100% | 2025-04-01 | 2025-04-07 | bar: April WK1 to April WK2
Evaluation
| Testing | All team members | 100% | 2024-03-08 | 2024-04-29 | bar: March WK3 to April WK4
| Debugging | Jonathan Ly Slate Colebank | 100% | 2024-04-08 | 2025-04-30 | bar: April WK2 to April WK4
| Address risks | Colson Swope Ripken Stork | 100% | 2024-05-01 | 2024-05-14 | bar: May WK1 to May WK2
| Presentation | All team members | 80% | 2024-05-15 | 2024-05-31 | bar: May WK3 to May WK4
Changes:
Added new task under execution: Move application to cyber range since all the current work is not able to be stored on the cyber range gitlab.
Updated progress percentages, we are now completely done with all initiation/planning tasks, now we are working through execution tasks
Formulas:
START = [END, row above]
END = [START]+2

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.